## Sheet1
TEST SUMMARY
| Field | Details
| Project Name | AI CERTs Learner Portal
| Tested By | Sanika Mandaokar
| Date | 2025-10-23
| Total Test Cases | 56
| Passed | 51
| Failed | 5
| Blocked | 0
| Test Type | Manual Testing
| Environment | Web Browser (Chrome,Edge,Brave)
| Tools Used | Excel Sheet
| Severity | Major issues found were mostly validation related ; no critical defects observed
| Priority | High(validation and navigation fixes needed before public releases
| Comments | Found minor validation and navigation issues
BUG REPORT
Bug Id | Module | Test Case Id | Bug Title | Steps To Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Comments
BUG_01 | Step 2- Sign Up as a new user | TC_09 | First Name field accepts special characters and numbers | 1.Open Browser 2.Enter Portal Url 3.Click on sign up 4.Enter "123@456$" in First Name textfield | First name text field should not accept the input and error message should be displayed | Field accepts input without error; no validation message shown | Major | High | Open | Validation issue found
BUG_02 | Step 2- Sign Up as a new user | TC_13 | Last Name field accepts invalid input | 1.Open Browser 2.Enter Portal Url 3.Click on sign up 4.Enter "abc@12$rt" in Last Name textfield | Last Name text field should not accept the input and error message should be displayed | Field accepts input; error message not displayed | Major | High | Open | Validation issue found
BUG_03 | Step 2- Sign Up as a new user | TC_17 | First and Last Name fields accept same valu | 1.Open browser 2.Enter Portal url 3.Click on signup button 4.Enter same data in both first and last name text field | First and last name textfield should not accept same data and error message should be displayed as 'First and Last Name' cannot be same | No error displayed, form allows same values | Major | High | Open | Should display validation error
BUG_04 | Step 2- Sign Up as a new user | TC_30 | Cancel button redirects instead of clearing form | 1.Go to Signup for free course page 2.Fill in all the valid details 3.Click on cancel button | All the data entered should be cleared and the user remains on the same page | Form data not cleared, redirected to login | Major | High | Open | User flow and usability impact
BUG_05 | Step 3- OTP Verification | TC_42 | OTP system does not block after wrong attempts | 1.Go to Otp verification screen 2.Enter incorrect otp and click on submit button 3.Repeat the process until you have entered the wrong otp five times 4.Try to enter otp again after hitting the attempt limit | After five incorrect OTP attempts, the portal should block further attempts, either by disabling the OTP input or showing an error message like “You have exceeded the maximum number of attempts. Please try again later” or “Contact support to continue.” | Further OTP attempts are still allowed | Critical | High | Open | Security/usability risk
Module Name : Step 1 – Access the Portal
Version : 1.1
Test Case Id | Test Scenario | Preconditions | Test Steps | Input | Expected Result | Actual result | Status | Comments
TC_01 | To verify that when user enters the app url in the browser ,welcome page is displayed | Browser Installed | 1.Open web browser 2.Enter url | https://v2learner.aicerts.ai/ | Welcome page should be displayed |  | Pass
TC_02 | To verify that the portal laods correctly on all the browsers such as chrome, firefox, edge , safari, brave | Browser Installed | 1.Open web browser individually 2.Enter url on all the browsers | https://v2learner.aicerts.ai/ | Welcome page should be displayed |  | Pass
TC_03 | To verify that when user enters inavlid portal url , error message is displayed | Browser Installed | 1.Open web browser 2.Enter inavlid url | https://v3Learner.aicerts.ai/ | Error message should be displayed as 'Page not found' or a similar error |  | Pass
TC_04 | To verify that the portal responds properly under slow network conditions. | The tester should have a browser (like Chrome DevTools) that supports network throttling. | 1.Slow down the network speed 2.Enter portal url | https://v2learner.aicerts.ai/ | A loading indicator should appear, and the page should load successfully after a short delay ie .without freezing or showing errors. |  | Pass
Module Name : Step 2 - Sign Up as a New User
Version : 1.2
Test Case Id | Test Scenario | Preconditions | Test Steps | Input | Expected Result | Actual Result | Status | Comments
TC_05 | To verify that when user click on 'Sign Up' button the user is redirected to registration page | User is on welcome page | 1.Open Browser 2.Enter portal Url 3.Click on Sign Up | NA | The registration page should open successfully with correct title and form fields |  | pass
TC_06 | To verify that all the mandatory fields are marked with asterisk(*) and is displayed | User is on sign up page | 1.Open Browser 2.Enter portal Url 3.Click on Sign Up | NA | All the mandatory fields should be marked with asterisk sign in red colour and is displayed |  | Pass
TC_07 | To verify that 'First Name' text field should only accept only alphabets | User is on sign up page | 1.Open Browser 2.Enter portal Url 3.Click on Sign Up 4.Enter some alphabets in first name text field | abcdef | First name text field should accept the input and error message should not be displayed |  | Pass
TC_08 | To verify that 'First Name' text field should not accept only numbers | User is on sign up page | 1.Open browser 2.Enter portal url 3.Click on sign up 4.Enter some numbers in First name text field | 123456 | First name text field should not accept the input and error message should be displayed |  | Pass
TC_09 | To verify that 'First name' text field should not accept combination of special characters and numbers | User is on sign up page | 1.Open browser 2.Enter portal url 3.Click on sign up 4.Enter combination of special characters and numbers in First name text field | 123@456$ | First name text field should not accept the input and error message should be displayed |  | Fail
TC_10 | To verify that 'First name' text field should 'First name' text field should not accept blank spaces | User is on sign up page | 1.Open Browser 2.Enter portal url 3.Click on signup button 4.Do not enter anything in the first name text field | NA | Alert message shoulf be displayed as 'Please fill out this field' |  | Pass
TC_11 | To verify that when user enters more than 30 characters in 'First name' text field an alert should be displayed | User is on sign up page | 1.Open Browser 2.Enter portal url 3.Click on signup button 4.Enter more than 30 characters in first name text field | abcdefgyhikjhtrefghutyhnbghuikrt | Alert message should be displayed as 'Signup Failed! First and last name can be up to 30 characters each.' |  | Pass
TC_12 | To verify that 'Last Name' Text field should accept only alphabets | User is on sign up page | 1.Open Browser 2.Enter Portal Url 3.Click on signup button 4.Enter some alphabets in last name text field | aduhbmke | Last Name text field should accept the input and error message should not be displayed |  | Pass
TC_13 | To verify that 'Last Name' Text field should not accept combination of special characters, numbers and alphabets | User is on sign up page | 1.Open browser 2.Enter portal url 3.Click on signup button 4.Enter combination of alphabets,numbers and special characters | abc@12$rt | Last Name text field should not accept the input and error message should be displayed |  | Fail
TC_14 | To verify that when user enters more than 30 characters in 'last Name' text field an alert should be displayed | User is on sign up page | 1.Open Browser 2.Enter portal url 3.Click on signup button 4.Enter more than 30 characters in first name text field | abcdefgyhikjhtrefghutyhnbghuikrt | Alert message should be displayed as 'Signup Failed! First and last name can be up to 30 characters each.' |  | Pass
TC_15 | To verify that in 'Last Name' text field when user enters invalid data and wants to delete backspace should work | User is on sign up page | 1.Open Browser 2.Enter Portal Url 3.Click on signup button 4.Enter some invalid data in last name text field and try to delete it using backspace | abshhidu8ou | Backspace should work correctly and input should be deleted |  | Pass
TC_16 | To verify that in 'Last Name' text field user should be able to copy-paste | User is on sign up page | 1.Open browser 2.Enter portal url 3.Click on signup button 4.Try to copy-paste in last name text field | NA | Copy-Paste should work properly and input should be entered |  | Pass
TC_17 | To verify that when user enters same data in 'First Name' and 'Last Name' textfield ,error should be displayed | User is on sign up page | 1.Open browser 2.Enter Portal url 3.Click on signup button 4.Enter same data in both first and last name text field | First Name : Rohini Last Name: Rohini | First and last name textfield should not accept same data and error message should be displayed as 'First and Last Name' cannot be same |  | Fail
TC_18 | To verify that 'Email' and 'Confirm Email' text field should accept valid mail Id format | User is on sign up page | 1.Open browser 2.Enter Portal Url 3.Click on Signup button 4.Enter valid email id | rohini75@gmail.com | Email textfield should accept the valid input and error message should not be displayed |  | Pass
TC_19 | To verify that 'Email' and 'Confirm Email' text field should not accept existing mail Id | User is on sign up page | 1.Open Browser 2.Enter portal url 3.Click on signup button 4.Enter existing email id | rohini75@gmail.com | Email textfield should not accept existing email id and error message should not be displayed as 'Signup Failed! Email already registered.' |  | Pass
TC-20 | To verify that 'Email' and 'Confirm Email' text field should not accept multiple mail Id's | User is on sign up page | 1.Open Browser 2.Enter portal url 3.Click on signup button 4.Enter two email id's | Email: rohini75@gmail.comrohan@gmail.com | Email and Confirm Email textfield should not accept the input and error message should be displayed ' |  | Pass
TC_21 | To verify that 'Email' and 'Confirm email' text field cannot be different and error message is displayed | User is on sign up page | 1.Open Browser 2.Enter portal url 3.Click on signup Button 4.Enter different email id's | Email : rohini75@gmail.com Confirm Email : rohini75567@gmail.com | Email and Confirm Email textfield should not accept the input and error message should be displayed as 'Email do not match.' |  | Pass
TC_22 | To verify that if user enters same email id in both Email and Confirm Email textfield , It should accept the input | User is on sign up page | 1.Open Browser 2.Enter portal url 3.Click on signup button 4.Enter email ending with domain .com | Email : rohini75@gmail.com Confirm Email : rohini75@gmail.com | Email textfield should accept the valid input and error message should not be displayed |  | Pass
TC_23 | To verify that 'I agree to the Privacy Policy and Terms and conditions' checkbox is displayed and unchecked by default | User is on sign up page | 1.Open Browser 2.Enter portal url 3.Click on sign up | NA | Checkbox is displayed successfully and is unchecked initially |  | Pass
TC_24 | To verify that user is not able to submit the signup form without checking the agreement checkbox | User is on sign up page | 1.Open browser 2.Enter portal url 3.Click on signup button 4.Fill all the fields correctly and do not check the checkbox 5.Click on 'signup for free course | NA | Form should not be submitted and error message should be displayed as 'Please check this box if you want to proceed' |  | Pass
TC_25 | To verify that when user click on 'Privacy Policy' and "Terms and conditions" link ,link opens the correct document and opens in a new tab | User is on sign up page | 1.Open Browser 2.Enter portal url 3.Click on signup button 4.click on Privacy policy | NA | Privacy policy and terms and conditions links opens in a new browser tab and policy contents is displayed successfully |  | Pass
TC_26 | To verify that “Sign up for Free Course” button is visible, properly aligned, and is clickable. | User is on sign up page | 1.Open browser 2.Enter portal url 3.Click on signup | NA | Sign Up botton is visible in the end , properly aligned , and it is clickable |  | Pass
TC_27 | To verify the response time , when user fill all the details and ckick on sign up button , the form should submit within short period of time with valid data | User is on sign up page | 1.Open browser 2.Enter portal url 3.Click on signup | NA | After submitting the form the page should respond within 2-3 seconds and otp verification page should be displayed |  | Pass
TC_28 | To verify that sign up page loads correctly on different browsers such as chrome ,edge etc | User is on sign up page | 1.Open Browser 2.Enter Portal url 3.Open signup page on different browsers | NA | The portal opens successfully in all the browsers and navigate to signup page |  | Pass
TC_29 | To verify that "Cancel" button is visible, aligned properly and is clickable | User is on sign up page | 1.Open browser 2.Enter portal url 3.Click on signup | NA | Cancel button is visible ,properly aligned and it is clickable |  | Pass
TC_30 | To verify that when user clicks on Cancel Button , it clears all the data entered in the form without redirescting the user away from the Sign Up page | User is on sign up page | 1.Go to Signup for free course page 2.Fill in all the valid details 3.Click on cancel button | NA | All the data entered should be cleared and the user remains on the same page |  | Fail
Module Name : Step 3 – OTP Verification
Version : 1.3
Test Case Id | Test Scenario | Preconditions | Test Steps | Input | Expected Result | Actual Result | Status | Comments
TC_31 | To verify that when user enters all the correct details on signup page and click on signup button ,user should be rediected to Otp verification page | Registration form submitted | 1.Open browser 2.Enter portal url 3.Enter all the details 4.Click on signup button | NA | User should be registered successfully and user should be navigated to Otp verification page and is displayed |  | Pass
TC_32 | To verify that once the user is registered the otp should be sent to user's registered email id | User is on Otp screen | 1.Open signup page 2.Register using email id 3.Go to email and check inbox | NA | Otp mail is received on users registered email id with correct code and format |  | Pass
TC_33 | To verify that Otp text field should only accept numbers | User is on Otp screen | 1.Go to Otp verification page 2.Enter numbers in otp text field | 1234 | Otp should be accepted and it should be a four digit otp , and error message should not be displayed |  | Pass
TC_34 | To verify that Otp text field should not accept combination of numbers,alphabets and special characters | User is on Otp screen | 1.Go to Otp verification page 2.Enter combination of numbers,alphabets and special characters in otp text field | 12@5sar$ | Otp should not be accepted and error message should be displayed as 'Invalid or outdated otp' |  | Pass
TC_35 | To verify that when user enters correct otp which is received on registered email id and click on submit button , user should be navigated to learner dashboard | User is on Otp screen | 1.Go to otp verification page 2.Go to email, check inox or spam 3.Copy otp and paste in otp text field 4.Click on submit button | 1234 | Otp should be accepted and user should be navigated to learner portal |  | Pass
TC_36 | To verify that when user enters incorrect ,expired Otp or leave the field blank ,error message is displayed | User is on Otp screen | 1.Go to otp verification page 2.Enter incorrect,expired otp in otp text field 3.Click on submit button | 5678 | Error message should be displayed as 'Inavlid or Outdated otp' |  | Pass
TC_37 | To verify that when user click on 'Resend Otp' option , otp should be resent to user's registered email id | User is on Otp screen | 1.Click on otp verification page 2.click on resend otp option | NA | New Otp should be send to user's registered email id |  | Pass
TC_38 | To verify that when clicked on 'Contact Support' option 'Contact site support' form should be opened | User is on Otp screen | 1.Click on otp verification page 2.click on Contact Support option | NA | User should be redirected to Contact site support page and form should be opened in the same tab |  | Pass
TC_39 | To verify that once the user receives an Otp, there is a 1-minute countdown before they can click the 'Resend Otp' option | User is on Otp screen | 1.Go to otp verification page 2.Once otp is sent , observe 'resend otp' option | NA | The portal should display a visible countdown timer (showing seconds or a message like “Resend OTP in 60 seconds”). During this time, the “Resend OTP” button is disabled and cannot be clicked. Once the timer finishes (after 1 minute), the button is active and the user can request a new OTP. |  | Pass
TC_40 | To verify that Otp screen loads and functions well on all major browsers such as chrome , edge, brave etc | User is on Otp screen | 1.Open otp verification screen on different browser and check the behaviour | NA | Otp verification page works same on all the browsers |  | Pass
TC_41 | To verify that otp can be used only once | User is on Otp screen | 1.Open otp verification page 2.Enter the received otp and click on submit button 3.Re-enter same otp and click on submit button | 1245 | Enter otp field should not accept same otp which is used eariler and error message should be displayed |  | Pass
TC_42 | To verify that after entering the wrong Otp for too many times (for example : 5 times), the system blocks further attempts | User is on Otp screen | 1.Go to Otp verification screen 2.Enter incorrect otp and click on submit button 3.Repeat the process until you have entered the wrong otp five times 4.Try to enter otp again after hitting the attempt limit | 1234 | After five incorrect OTP attempts, the portal should block further attempts, either by disabling the OTP input or showing an error message like “You have exceeded the maximum number of attempts. Please try again later” or “Contact support to continue.” |  | Fail
Module Name : Step 4 – Dashboard & Course Access
Version : 1.4
Test Case Id | Test Scenario | Preconditions | Test Steps | Input | Expected Result | Actual Result | Status | Comments
TC_43 | To verify that once the otp is verified ,user should be navigated to 'Learner dashboard' with a message as 'welcome back ,user_name' | User is logged in | 1.Verify otp 2.Click on submit button | NA | Otp should be verified successfully and user should be redirected to Learner Dashboard |  | Pass
TC_44 | To verify that 'My Courses' section should be visible on the learner dashboard | User is on Learner Dashboard | 1.Verify otp 2.Click on submit button 3.On dashboard look for "my courses" section | NA | “My Courses” section is displayed on the dashboard. |  | Pass
TC_45 | To verify that when user clicks on 'My Courses' section, "AI+foundation" course is listed and is be visible on the learner dashboard | User is on Learner Dashboard | 1.Verify otp 2.Click on submit button 3.On "my courses" section look for "AI+Foundation" course | NA | "AI+Foundation" course is listed and visible on the learner dashboard |  | Pass
TC_46 | to verify that when user clicks on 'View Course' button it opens the learning content including videos ,Ebook etc | User is on Learner Dashboard | 1.Verfiy otp 2.Click on submit button 3.On learner Dashboard click on view course | NA | User should be able to click on view course button and learning content should open |  | Pass
TC_47 | To verify that in the header of Learner dashboard several options like my courses ,my certifications, contact us , search bar, should be present | User is on Learner Dashboard | 1.Verify Otp 2.Click on submit button 3.Observe the learner dashboard | NA | In learner Dashboard ,user should be able to see options like my courses,my certifications etc |  | Pass
Module Name : Step 5 – Course Detail Page & Learning Modes
Version : 1.5
Test Case Id | Test Scenario | Precondition | Test Steps | Input | Expected Result | Actual Result | Status | Comments
TC_48 | To verify that when user clicks on "View Course", user should be redirected to "Course Detail Page"(AI+Foundation) | User is on learner Dashboard | 1.On learner page look for course details button 2.Click on view course button | NA | User should be navigated to Course detail page and course details should be displayed |  | Pass
TC_49 | To verify that all the learning modes such as video,audio,Podcast and E-book is displayed on the top-right of the Course details page | User is on Course details page | 1.On learner dashboard page look for 'view course' button 2.Click on view course button 3.Observe the learning modes in course details page | NA | All the learning modes such as video,audio,E-book and Podcast should be displayed in the Top-right of the page |  | Pass
TC_50 | To verify that when user selectl the learning modes such as video,audio,Podcast and E-book one by one ,each learning mode updates the index panel | User is on Course details page | 1.On learner dashboard page look for 'view course' button 2.Click on view course button 3.Observe the learning modes index panel | NA | Index panel should update according to the selected mode as user selects the learning mode |  | Pass
TC_51 | To verify that when user selectl the learning modes such as video,audio,Podcast and E-book one by one ,each learning mode content type updates and loads correctly | User has selected a learning mode | 1.Come to Course details page 2.Select all the learning modes one by one and observe the content | NA | The content should be displayed correctly acoording to the selected modes without any errors |  | Pass
TC_52 | To verify that the when user navigates between modules and lessons ,it works properly | Content is loaded for any learning mode | 1.Go to Learning modes 2.Select each mode one by one 3.Navigate through multiple modules and lessons | NA | Naviagtion updates the content correctly without any issues or errors |  | Pass
TC_53 | To verify that common activities or quizzes appear and remain accessible across all four modules | Modules with activities or quizzes available | 1.Go to Learning modes 2.Select each mode one by one 3.Access quizzes or activities in each mode | NA | Activities or quizzes are displayed correctly in all the modules and function correctly in all the modes |  | Pass
TC_54 | To verify that the video and audio players allow the user to use Play, Pause, Mute, Unmute, and Fullscreen controls without any errors | video and audio mode selected with media content | 1.Click on course details page , select alesson that has video and audio content 2.Click play and confirm the media starts 3.Click pause and confirm the media stops 4.Click play again and check the playback resumes from where you left off 5.Click mute to turn off the sound and unmute to turn the sound back on 6.Click the fullscreen button to expand the player to fill the screen and exit fullscreen to return to normal view | NA | All playback controls (Play, Pause, Mute, Unmute, Fullscreen) should work smoothly for both video and audio. The media should respond immediately and correctly to each action, with no glitches or unexpected behavior. |  | Pass
TC_55 | To verify that quickly switching between different learning modes (Video, Audio, Podcast, E-book) loads content properly and does not cause any errors or blank screens. | User switches between modes multiple times | 1.Open course details page 2.Select each learning mode (video,audio,Podcast ,E-book) one by one 3.Check for any errors or blank screens | NA | Each time you switch to a different mode, the content loads normally. No error messages or blank screens should appear at any point during mode switching. |  | Pass
TC_56 | To verify that "help video " button is present in the header section in right-top , and when user clicks on it LMS learning guide page should apper with a help video | User is on Course details page | 1.Open course details page 2.Click on help video button | NA | User should be navigated to LMS learning guide page and help video should be displayed |  | Pass